Ownership clarity needs correcting to avoid reporting and follow-up risk.

---

### Client: Charlotte Morrison

| Field | Detail |

|---|---|

| Client | Charlotte Morrison |

| Lender | Not specified |

| Current stage | Not recognised during review; ownership/status needs confirmation |

| Owner | Paul |

| Deadline | Not specified |

#### Current Position

Charlotte Morrison was not recognised during the review and needs ownership/status confirmation.

#### Risks / Blockers

- Case may drift without clear owner.

- CRM may be inaccurate.

- Follow-up may be missed.

#### Actions Required

- Confirm status and ownership.

- Update CRM with next step.

#### Action Owner

- **Adviser:** Paul Banyard

#### Trend Insight

**Stagnant.**

The case cannot be controlled until ownership and status are confirmed.

---

## 5. Protection In Progress

### Current Position

Protection is the main performance concern.

The review identified:

- Quarterly protection target: **8 insurance applications**

- Current position: **1 insurance application**

- Shortfall: **7 insurance applications**

- Mortgage applications: **6**

- Protection applications: **1**

- Protection conversion: **16%**

The 21-day protection callback report shows a large number of opportunities requiring attention. Protection activity is materially behind target and not being driven with the same focus as mortgage business.

### Vs Last Week / Last Month

No full prior comparison was provided, but the recurring issue is that protection callback tracking was not fully updated before the review, and protection activity remains below expectation.

### Protection Cases Discussed

| Client | Current Position | Issue / Risk | Owner |

|---|---|---|---|

| Raymond | Existing IP, life and critical illness cover previously sold. Remortgage case reverted to product transfer after down valuation due to property being above commercial. No known change in circumstances. Protection review still to be followed up. | Review not yet booked; missed opportunity to confirm ongoing suitability. | Paul / Admin |

| Claire and Callum | Employer benefits details still required before proper protection review. Sean was following up. | Protection review cannot be completed without benefits details. | Sean |

| Tatiana | Protection review required with Tatiana and her mother after mortgage review and completion. | Client not yet booked; adviser follow-up may not be best use of time and should be assigned for booking where appropriate. | Paul / Admin |

| Tomlinson | Insurance already completed. | Tracker needs updating to avoid duplicate chase. | Paul |

| Gilroy | Callback booked for **29 May 2026**. | Must ensure appointment proceeds and outcome is logged. | Paul |

| Burgess | Callback booked for **28 May 2026 at 12:30**. | Entry was initially placed under Smith, creating CRM accuracy risk. | Paul |

| Smith | Incorrect entry made under this client during tracker update. | Wrong client record and follow-up risk. | Paul |

| Fergus Gain / Fergus Kane | Outstanding health questions and possible application submission status. | Protection application may stall or be lost. | Paul |

| Stephen Reed / Stevenson | Appeared on 21-day / protection list. | Ownership/status unclear. | Paul |

### Cases Without Protection Discussion / Missed Cross-Sell Opportunities

- Protection is not being mirrored alongside mortgage activity.

- Raymond’s ongoing protection suitability review has not yet been booked after remortgage / product transfer activity.

- Tatiana’s protection review with her mother remains outstanding after mortgage review and completion.

- Claire and Callum cannot progress until employer benefits details are obtained.

- Fergus Gain / Fergus Kane has unresolved health question and application status issues.

- The 21-day callback report contains further opportunities that need to be worked quickly.

### What’s Working Well

- At least **1 protection application** is recorded.

- Protection opportunities exist within the callback reports.

- The gap is visible and measurable.

- Some protection callbacks are now booked.

- Paul is identifying protection opportunities through workflow review.

- Existing client protection positions are known in some cases, such as Raymond.

- This is a known focus area for Paul and the wider team.

### What’s Not Working Well

- Protection conversion is low at **16%**.

- Paul has only **1 protection application** from **6 mortgage applications**.

- Protection is not being given the same focus as mortgage activity.

- Protection callbacks are not being acted on quickly enough.

- Protection tracking was not fully updated before the meeting.

- Some protection reviews are still not booked.

- There is over-reliance on adviser follow-up where admin booking support may be more efficient.

- Opportunities become harder to convert the longer they are left.

### Risks / Blockers

- Gap between **1 current insurance application** and the **8-application quarterly target** is significant.

- Protection business may be missed if callbacks are delayed.

- Delayed reviews reduce written business and create revenue shortfall.

- Longer delays make clients harder to re-engage.

- Paul is unlikely to write the required protection business for May 2026.

- Future revenue is exposed if protection does not catch up in June 2026.

- Weak tracking may cause duplicate chases, missed reviews or unclear ownership.

- CRM inaccuracy may hide the true position if callbacks and application statuses are not updated.

### Actions Required

- Prioritise the 21-day protection callback report.

- Review all outstanding protection callbacks.

- Chase and book outstanding protection reviews.

- Assign booking tasks to admin where appropriate.

- Complete booked protection appointments and update CRM outcomes immediately.

- Ensure protection is chased alongside purchase and remortgage activity.

- Resolve the Fergus Gain / Fergus Kane protection task.

- Build protection activity into the June 2026 pipeline plan.

- Identify the next **3 protection cases** for June 2026.

### Action Owner

- **Adviser:** Paul Banyard — protection follow-up, CRM updates, callback outcomes and pipeline planning.

- **Admin:** Admin support where booking is required.

- **Case Manager / Admin:** Sean for Claire and Callum employer benefits follow-up.

### Trend Insight

**Declining.**

Protection activity is materially behind target. With only **1 protection application from 6 mortgage applications**, conversion is weak and delayed callbacks are increasing the risk of missed business.

---

## 6. Written Business – This Month

### Current Position

| Metric | Current Position |

|---|---:|

| Mortgage written business | **£2,792.26** |

| Protection written business | Approximately **£1,100** |

| Purchase applications | **3** |

| Renewal applications | **4** |

| Protection applications | **1** |

| Banked business | **£4,140.81** |

| Purchase application target | **5** |

| Purchase application shortfall | **2** |

| Required written number for May 2026 | **17** |

| Expected result | Bob stated Paul is **not going to write the 17 required this month** |

Bob stated that Paul is broadly **in line to hit the number of mortgages needed**, but this remains **hit or miss by the end of May 2026** and depends on documents being received and progressed.

Paul confirmed there are potentially **2 further purchase cases**, but one is still dependent on documents being received.

### Written vs Same Month Last Year

No same-month-last-year written business comparison was provided.

### Pipeline Expected to Write

- Two potential purchase cases may close the immediate purchase shortfall.

- One of those cases is still dependent on documents.

- Some mortgage cases expected in May 2026 may slip into June 2026.

- Mortgage numbers remain potentially achievable, but protection is materially behind.

### Likelihood of Target Being Hit

- Purchase case target may still be reached if the two potential cases proceed.

- Overall written target of **17** is not expected to be achieved.

- Protection target is significantly behind and unlikely to recover fully before month end.

### Adviser Confidence Level

- Paul identified potential purchase cases but acknowledged document dependency.

- Bob described mortgage delivery as “hit or miss” by month end.

- Paul described the current pipeline as having “no quick wins”.

### Reasons for Performance Difference

- Appointment volume is strong, but conversion is slow.

- Document delays are holding back some cases.

- Protection activity is weak.

- Reporting breakdown was not prepared clearly before the review.

- Some cases were not in the correct CRM workflow stage.

- CRM tasks and next steps need tighter ownership.

### What’s Working Well

- Paul has identified two potential purchase cases that may close the gap.

- Paul is aware that one case is waiting on documents.

- Mortgage numbers are close enough to target to remain achievable.

- Appointment volume supports future written business.

- Some cases expected to write in May 2026 may support June 2026 if they slip.

### What’s Not Working Well

- Written business is not converting quickly enough from appointment volume.

- May 2026 target of **17** is not expected to be achieved.

- Protection written business is not strong enough.

- Document delays may affect whether mortgages land in-month.

- Reporting breakdown was not prepared clearly before the review.

### Risks / Blockers

- If the two potential purchase cases do not proceed, written business will remain below expectation.

- Waiting on documents may delay submission and push business into June 2026.

- Protection shortfall may increase pressure in June and July 2026.

- Slipped business may not materialise if active prospects are not managed well.

- Continued underperformance in protection will increase pressure on future months.

### Actions Required

- Chase documents on the purchase case currently waiting.

- Push the two potential purchase cases to application where appropriate.

- Focus on cases where documents are outstanding.

- Ensure document review tasks are sitting with the correct owner, such as Sean where appropriate.

- Progress ready cases to recommendation and application.

- Keep written business tracker updated by product type:

- Purchases

- Renewals

- Protection

- Build a June 2026 catch-up plan, including additional mortgages and protection cases.

### Action Owner

- **Adviser:** Paul Banyard

- **Case Manager / Admin:** Sean where document review is required.

### Trend Insight

**Stagnant.**

There is potential business available, but conversion depends on faster document collection, clearer tracking, stronger follow-up and improved protection activity.

---

## 7. Banked Business – This Month

### Current Position

Banked business was reviewed at **£4,140.81**.

### Banked vs Last Year

No banked business comparison with the same month last year was provided.

### Pipeline Still to Complete

- Written mortgage cases still need to improve to support future banked business.

- Purchase pipeline includes two potential cases, one dependent on documents.

- Cases slipping from May 2026 may support June 2026 if managed properly.

### Slippage Risk

- If written business does not improve, future banked business will be exposed.

- Document delays could push written and future banked income into later periods.

- Weak protection conversion reduces future income potential.

### Revenue Exposure

- Banked figure is known, but product-level breakdown needs to be clearer.

- Without clean reporting, it is harder to forecast slippage or understand which product types are driving income.

### What’s Working Well

- Banked figure is known and was confirmed during the meeting.

### What’s Not Working Well

- Banked business report was not prepared in advance in a structured way.

- Product-level breakdown needs to be clearer.

- Written and banked reporting discipline needs improvement.

### Risks / Blockers

- Forecasting is weaker without clean reporting.

- Future banked business is exposed if written business does not improve.

- Slippage risk cannot be properly managed without product-level reporting.

### Actions Required

- Keep banked reporting updated.

- Break down banked and written figures by product type before the next review.

### Action Owner

- **Adviser:** Paul Banyard

### Trend Insight

**Stagnant.**

The current banked figure is clear, but reporting discipline and product-level breakdown need to improve.

---

## 8. Renewal / Remortgage Income

### Current Position

Renewal and remortgage activity was discussed as part of the business mix and pipeline review.

Current month-to-date mortgage mix includes:

- **4 renewal cases**

- **3 purchase cases**

- **1 protection application**

Bob also raised the need to understand expected income from the remortgage workflow.

### Clients / Cases in Pipeline

| Client / Area | Current Position | Issue / Risk | Owner |

|---|---|---|---|

| Raymond | Remortgage case reverted to product transfer after down valuation due to property being above commercial. | Protection review still needs follow-up. | Paul / Admin |

| Remortgage workflow | Expected income not clearly quantified. | June 2026 income forecast is uncertain. | Paul |

| Purchase / renewal reporting | Renewal cases identified during the review. | Product-level reporting was not prepared in advance. | Paul |

### Reviews Booked

- Protection callbacks booked for Burgess and Gilroy.

- No specific remortgage review booking schedule was provided beyond Raymond and general workflow review.

### Insurance Gaps

- Raymond requires protection review follow-up despite existing IP, life and critical illness cover.

- Protection should be reviewed alongside remortgage and product transfer activity.

- General protection conversion is weak at **16%**.

### Clients Still to Contact

- Raymond protection review follow-up.

- Remortgage workflow opportunities need review.

- 21-day protection callback opportunities need prioritising.

### Forecast vs Expectation

- Remortgage workflow expectations were not clearly quantified.

- Bob highlighted the need to review remortgage workflow opportunities to support June 2026 income.

### What’s Working Well

- Renewal cases were identified during the review.

- Raymond’s position is understood.

- Remortgage workflow was identified as an area for income review.

### What’s Not Working Well

- Remortgage income expectations were not quantified.

- Product-level reporting was not prepared in advance.

- Protection reviews are not consistently being completed alongside remortgage activity.

### Risks / Blockers

- Income forecast for June 2026 remains uncertain.

- Insurance opportunities may be missed on remortgage / product transfer clients.

- Weak reporting makes it harder to identify income drivers.

### Actions Required

- Review remortgage workflow opportunities.

- Quantify expected remortgage income.

- Follow up Raymond’s protection review.

- Ensure protection is reviewed alongside remortgage and renewal activity.

### Action Owner

- **Adviser:** Paul Banyard

- **Admin:** Admin support for booking where appropriate.

### Trend Insight

**Stagnant.**

Renewal and remortgage activity exists, but income expectations and associated protection opportunities need clearer ownership and reporting.

---

## 9. Remortgage Opportunities

### Current Position

Remortgage opportunities were discussed primarily through Raymond and the wider remortgage workflow.

### Clients Chased / Disengaged / Re-Engagement Strategy

| Client / Area | Position | Required Re-Engagement |

|---|---|---|

| Raymond | Remortgage reverted to product transfer after down valuation due to property being above commercial. Existing protection in place. | Follow up protection review to confirm suitability and identify any changes. |

| Remortgage workflow | Expected income not clearly quantified. | Review CRM workflow and identify opportunities for June 2026. |

### Weak Follow-Up Trends

- Protection is not being consistently chased alongside remortgage / mortgage activity.

- Remortgage workflow expectations are not clearly reported.

- Callback and review tracker discipline is weak.

### What’s Working Well

- Raymond’s revised route to product transfer is understood.

- Remortgage workflow has been identified as an area to review.

### What’s Not Working Well

- Protection follow-up after remortgage / product transfer activity remains incomplete.

- Expected remortgage income has not been quantified.

- CRM and tracker records are not consistently updated.

### Risks / Blockers

- Remortgage income may be under-forecast or missed.

- Protection cross-sell opportunities may be delayed or lost.

- Clients may drift if re-engagement is not diarised.

### Actions Required

- Review remortgage workflow opportunities.

- Follow up Raymond protection review.

- Ensure all remortgage-related next steps are logged in CRM.

- Use admin booking support where appropriate.

### Action Owner

- **Adviser:** Paul Banyard

- **Admin:** Admin support where booking is needed.

### Trend Insight

**Stagnant.**

Opportunities exist, but they are not yet being actively quantified or consistently linked to protection review activity.

---

## 10. Projected Income

### Current Position

Bob highlighted the need for Paul to think ahead about the pipeline required for June 2026.

The focus should be on creating the next:

- **6 mortgage cases**

- **3 protection cases**

Bob also raised the need to understand expected income from the remortgage workflow.

### Pipeline vs Budget

- Appointment volume is strong, with **44 appointments** against an expectation of **40**.

- May 2026 written target of **17** is not expected to be achieved.

- Purchase target is **5**, with **3** currently achieved and **2** potential cases identified.

- Protection target is **8 insurance applications** for the quarter, with only **1** currently achieved.

- June 2026 requires a clear pipeline plan for **6 mortgage cases** and **3 protection cases**.

### Shortfall

- Purchase cases are **2 short** of target.

- Protection applications are **7 short** of the quarterly target.

- May 2026 written business is expected to fall short of the required **17**.

- Protection conversion is only **16%**.

### Plan to Close Gap

- Progress the two potential purchase cases to application where appropriate.

- Chase outstanding purchase documents immediately.

- Prioritise the 21-day protection callback report.

- Identify the next **6 mortgage cases** for June 2026.

- Identify the next **3 protection cases** for June 2026.

- Review remortgage workflow opportunities.

- Maintain regular contact with active prospects.

- Use CRM workflows to delegate, diarise and move cases forward.

### Behaviour Impacting Results

- Cases are drifting where CRM workflow wording is unclear.

- Paul sometimes leaves tasks sitting rather than escalating or asking for help.

- Protection is not being given equal priority with mortgage activity.

- Reporting is reactive rather than prepared in advance.

- Active clients need stronger diary-led engagement.

### What’s Working Well

- Paul has active opportunities and strong appointment volume.

- Some May 2026 cases may slip into June 2026 and support next month’s starting pipeline.

- Protection callbacks exist and could still convert if worked quickly.

- Some mortgage numbers remain close enough to target to be achievable.

### What’s Not Working Well

- Future pipeline confidence is not yet strong enough.

- Protection activity is not keeping pace.

- Remortgage workflow expectations were not clearly quantified.

- Current behaviour risks leaving too much income dependent on cases drifting from one month to the next.

### Risks / Blockers

- Revenue shortfall if slipped mortgage cases do not convert.

- Protection income risk due to delayed callbacks.

- Pipeline uncertainty for June 2026.

- Failure to manage active prospects could affect mortgage and protection income.

- Poor CRM updates and overdue tasks increase the risk of cases drifting and income being delayed.

### Actions Required

- Identify pipeline for the next **6 mortgage cases**.

- Identify and prioritise the next **3 protection cases**.

- Review remortgage workflow opportunities.

- Build a June 2026 catch-up plan.

- Use CRM workflows to delegate, diarise and move cases forward.

### Action Owner

- **Adviser:** Paul Banyard

### Trend Insight

**Stagnant.**

There is opportunity in the pipeline, but income remains uncertain until Paul tightens follow-up, protection activity, reporting and workflow management.

---

## 11. Overall Performance Diagnosis

### Adviser Strengths This Week

- Strong appointment volume, with **44 appointments booked in May 2026** against an expectation of **40**.

- Positive client conversations.

- Mortgage case awareness is stronger than protection case control.

- Paul identified two potential purchase cases that may close the monthly purchase gap.

- Paul understands where some key protection cases sit once reviewed.

- Willingness to work through CRM workflow issues during the review.

- Mortgage numbers are still potentially in line with required levels.

- Paul identified case complexity, such as the self-build / land purchase enquiry for Ramesh.

- Some case-by-case improvements were made during the review.

### Main Risks

- Protection activity is well below target.

- Protection conversion is low at **16%**.

- Only **1 protection application** from **6 mortgage applications**.

- Protection is **7 applications short** of the quarterly target of **8**.

- May 2026 written business target of **17** is unlikely to be achieved.

- Purchase activity is **2 cases short** of target.

- CRM workflow discipline is inconsistent.

- Tracker and reporting preparation are not reliable enough.

- Overdue tasks create follow-up and ownership risk.

- Some case statuses and ownership positions were unclear.

- Active leads may drift without structured contact.

- Some workflow ownership gaps exist between adviser, admin and case manager until tasks are correctly assigned.

### Behaviour Patterns

- Mortgage activity is being prioritised ahead of protection.

- Reporting and tracking appear reactive rather than prepared in advance.

- There is reliance on memory instead of CRM accuracy.

- Paul sometimes takes workflow wording too literally rather than applying the logical next stage.

- Tasks can be left sitting where clarity is missing.

- Follow-up needs to become more structured and diary-led.

- Paul needs to use the system to delegate tasks to the correct owner rather than holding too much himself.

- There was hesitation around CRM workflow decisions.

- Where workflow options do not fit perfectly, tasks are at risk of being left unresolved rather than escalated or corrected.

### Accountability Concerns

- Paul must update DIP outcomes promptly.

- Paul must not allow tasks to become late because of uncertainty.

- Paul must complete outstanding passports and comments.

- Protection callbacks need faster action.

- CRM must show clear ownership and next steps.

- Paul must update business reporting before review rather than correcting during the meeting.

- Paul must ensure protection callback records are accurate and not entered under the wrong client.

### Where Management Support Is Required

- Bob to support Paul with workflow interpretation while Paul builds familiarity.

- Bob to provide referral details for Harry Connor / Buildstore.

- Paul should proactively ask Bob for help where CRM workflow is unclear.

- Continued support on using Midas / Platform reports correctly, especially reporting by product and adviser.

- Clarification on workflow routes where client journeys do not match obvious CRM options.

- Sean to support document review where tasks are assigned to him.

- Admin support should be used for booking protection reviews where adviser time is better spent progressing advice and applications.

### Focus for Next Week

- Clear all overdue workflow tasks.

- Keep CRM stages aligned to the real case position.

- Eliminate incorrect or misplaced tracker entries.

- Progress the two potential purchase cases to application where documents and advice allow.

- Chase outstanding documents immediately.

- Increase protection focus and book outstanding reviews.

- Prioritise the 21-day protection callback report.

- Update written and banked business by product type before the next review.

- Ensure every protection callback has a clear owner, date and outcome logged.

- Improve speed and consistency of follow-up with active clients.

- Eliminate CRM tasks sitting unresolved due to uncertainty.

- Progress stalled cases to the correct workflow stage.

- Complete outstanding passports, comments and protection updates.

- Identify the next **6 mortgage cases** and **3 protection cases** for June 2026.

- Ask for help before any CRM task falls overdue.

- Maintain office presence on core days where possible.

### Trend Insight

**Stagnant with areas improving, but protection declining.**

Paul’s appointment volume and mortgage opportunities are positive, and several cases improved during the review. However, CRM discipline, reporting preparation and protection activity are holding back performance. Protection is the clearest declining area because activity is materially behind target and callbacks are not being acted on quickly enough.

---

## 12. Master Action List

| Action | Client / Area | Owner | Deadline | Risk if not done |

|---|---|---|---|---|

| Update the 21-day spreadsheet fully | 21-day tracker | Paul Banyard | Not specified | Management reporting remains unreliable. |

| Update the protection callback tracker fully | Protection callbacks | Paul Banyard | Not specified | Missed reviews, duplicate chases or unclear ownership. |

| Correct inaccurate protection callback entries | Protection callbacks | Paul Banyard | Not specified | CRM remains inaccurate and follow-up may be missed. |

| Correct Burgess callback entry that was placed under Smith | Burgess / Smith | Paul Banyard | Not specified | Wrong client record and follow-up risk. |

| Attend and record outcome of Burgess callback | Burgess | Paul Banyard | **28 May 2026 at 12:30** | Protection opportunity may be missed. |

| Attend and record outcome of Gilroy callback | Gilroy | Paul Banyard | **29 May 2026** | Protection opportunity may be missed. |

| Follow up Raymond protection review after remortgage / product transfer activity | Raymond | Paul Banyard / Admin | Not specified | Missed suitability review and protection income opportunity. |

| Obtain employer benefits details for protection review | Claire and Callum | Sean | Not specified | Protection advice cannot be completed. |

| Arrange protection review with Tatiana and her mother | Tatiana | Paul Banyard / Admin | Not specified | Protection need remains unaddressed after completion. |

| Update Tomlinson as insurance already completed | Tomlinson | Paul Banyard | Not specified | Duplicate or unnecessary follow-up. |

| Correct Emily Irwin ownership from Roland to Paul | Emily Irwin | Paul Banyard | Not specified | Ownership and reporting remain inaccurate. |

| Confirm status / ownership of Charlotte Morrison | Charlotte Morrison | Paul Banyard | Not specified | Case may drift without clear owner. |

| Confirm ownership/status for Stephen Reed / Stevenson | Stephen Reed / Stevenson | Paul Banyard | Not specified | Protection or 21-day review opportunity may be missed. |

| Clear **5 overdue Platform tasks** dated **26 May 2026** | Platform workflows | Paul Banyard | Not specified | Missed follow-ups and SLA / CRM discipline risk. |

| Check application/status position | Fergus Kane / Fergus Gain | Paul Banyard | Not specified | Application may be delayed or incorrectly reported. |

| Review health questions and application status | Fergus Gain / Fergus Kane | Paul Banyard | Not specified | Protection application may stall or be lost. |

| Confirm whether protection application has been submitted and update CRM | Fergus Gain / Fergus Kane | Paul Banyard | Not specified | CRM may remain inaccurate and protection conversion risk increases. |

| Review active-looking status and update next step | Rachel | Paul Banyard | Not specified | Lead may stall. |

| Clarify DIP / debt-related workflow position | Robert Thurston | Paul Banyard | Not specified | Workflow and reporting remain inaccurate. |

| Complete Robert Thurston’s passport | Robert Thurston | Paul Banyard | Not specified | Case progression may be delayed once client re-engages. |

| Follow up with Robert Thurston | Robert Thurston | Paul Banyard | **2 June 2026** | Client may disengage and active buyer opportunity may drift. |

| Ensure DIP outcomes are updated promptly in CRM | All DIP cases | Paul Banyard | Ongoing | Reporting inaccuracies and stalled workflows. |

| Correct workflow route for reserved new-build client and mark documents required | New-build reserved client | Paul Banyard | Not specified | Case may sit in wrong stage and drift. |

| Send document request communication where not already sent | New-build reserved client / purchase cases | Paul Banyard | Not specified | Application cannot progress. |

| Complete adviser comments on the new-build / Megan’s friend case | Megan’s friend / new-build reservation case | Paul Banyard | Not specified | Case cannot progress smoothly to recommendation; documents and advice stage may stall. |

| Review documents and update adviser on missing items | Megan’s friend / new-build reservation case | Sean | Not specified | Recommendation booking may be delayed and missing documents may not be identified early. |

| Book recommendation once documents are complete and verified | Megan’s friend / new-build reservation case | Paul Banyard | Not specified | Application may be delayed and month-end written business may slip. |

| Send referral details for Harry Connor / Buildstore | Ramesh | Bob Duncan | Not specified | Client may not receive suitable self-build referral and may disengage. |

| Contact Ramesh with referral details and indicative fee guidance of roughly **£1,000**, subject to confirmation | Ramesh | Paul Banyard | Not specified | Client expectations may be unclear and opportunity may be lost. |

| Diarise and complete follow-up with Ramesh | Ramesh | Paul Banyard | **2 June 2026** | Client may drift and CRM follow-up may be missed. |

| Review whether standard nurture journey is appropriate for Ramesh given self-build nature | Ramesh | Paul Banyard / Anna | Not specified | Client may receive unsuitable communications. |

| Chase documents on purchase case awaiting paperwork | Purchase pipeline | Paul Banyard | Not specified | Purchase application may miss current month. |

| Progress two potential purchase cases to application where appropriate | Purchase pipeline | Paul Banyard | Not specified | Monthly purchase target remains short by 2 cases. |

| Break down written and banked business by product type before next review | Business return | Paul Banyard | Not specified | Performance reporting remains unclear. |

| Keep banked reporting updated | Banked business | Paul Banyard | Ongoing | Slippage and income forecasting remain weak. |

| Prioritise 21-day protection callback report | Protection pipeline | Paul Banyard | Ongoing | Protection conversion remains weak and income may be missed. |

| Identify next **6 mortgage cases** for June pipeline | Mortgage pipeline | Paul Banyard | Not specified | June 2026 pipeline may be insufficient. |

| Identify next **3 protection cases** for June pipeline | Protection pipeline | Paul Banyard | Not specified | Protection shortfall may continue into June 2026. |

| Review remortgage workflow opportunities | Remortgage pipeline | Paul Banyard | Not specified | June 2026 income forecast remains uncertain. |

| Maintain regular contact rhythm with active clients using calls, texts and emails | Active leads / pipeline | Paul Banyard | Ongoing | Positive conversations may not convert and clients may disengage. |

| Ask Bob for workflow help before tasks become overdue | CRM discipline | Paul Banyard | Ongoing | Tasks may fall late and cases may stall. |

| Maintain office presence on core days where possible | Adviser behaviour / availability | Paul Banyard | Ongoing | Reduced visibility and weaker client / team engagement. |

---

# Email Recap

**Subject:** Weekly Performance Review and Agreed Actions

Hi Paul,

Below is a summary of this week’s review and agreed actions.

## Follow-Up From Last Week

### Completed / Progressed Actions

- Some business figures were corrected and clarified during the review:

- Mortgage written business: **£2,792.26**

- Protection written business: approximately **£1,100**

- Banked business: **£4,140.81**

- The month-to-date case mix was clarified as:

- **4 renewal cases**

- **3 purchase cases**

- **1 protection application**

- Some protection callbacks are now booked:

- **Burgess** — **28 May 2026 at 12:30**

- **Gilroy** — **29 May 2026**

- Robert Thurston’s DIP was confirmed as passed and his status was updated to actively looking.

- The new-build / Megan’s friend case was moved into a clearer workflow position.

### Outstanding Actions

| Outstanding Action | Owner | Revised Deadline |

|---|---|---|

| Fully update the 21-day spreadsheet | Paul | Not specified |

| Fully update the protection callback tracker | Paul | Not specified |

| Correct inaccurate callback entries, including Burgess entered under Smith | Paul | Not specified |

| Clear **5 overdue Platform tasks** dated **26 May 2026** | Paul | Not specified |

| Break down written and banked business by product type | Paul | Before next review |

| Correct case ownership/status issues, including Emily Irwin, Charlotte Morrison and Stephen Reed / Stevenson | Paul | Not specified |

| Keep CRM workflows aligned to the real case position | Paul | Ongoing |

The same reporting and update discipline issues remain present. The data exists, but it is not being prepared or maintained in advance, which creates avoidable review time and weakens performance control.

## Performance Snapshot

- You have had **44 appointments booked in May 2026**, against an expected level of **40**.

- Lead volume is strong, but conversion is not yet following at the same pace.

- Mortgage written business is **£2,792.26**.

- Protection written business is approximately **£1,100**.

- Banked business is **£4,140.81**.

- Purchase applications are currently **3** against a target of **5**, leaving a shortfall of **2**.

- You identified **2 potential further purchase cases**, although one is dependent on documents.

- You are not expected to write the required **17** this month, so June 2026 needs a clear catch-up plan.

- Protection is the main concern:

- **6 mortgage applications**

- **1 protection application**

- **16% protection conversion**

- Quarterly protection target: **8 insurance applications**

- Current shortfall: **7 insurance applications**

## What Is Working

- Appointment volume is strong.

- There are positive client conversations taking place.

- You have visibility of two potential purchase cases that may close the immediate purchase gap.

- Mortgage case awareness is stronger than protection case control.

- Several active clients can form future pipeline if managed properly.

- Cases reviewed during the meeting were moved into clearer workflow positions.

- Robert Thurston’s DIP was confirmed as passed and his status updated to actively looking.

- Some protection callbacks are now booked.

## Identified Risks

- Protection activity is significantly behind target.

- Active leads may drift without regular contact.

- Protection callbacks are not being worked quickly enough.

- CRM tasks may fall overdue where workflow wording is unclear.

- DIP outcomes and next steps need to be updated more promptly.

- Written business from May 2026 may slip into June 2026 and needs careful management.

- Reporting and tracker preparation are still reactive rather than prepared in advance.

- Incorrect CRM entries and unclear ownership create follow-up and reporting risk.

## Cases Requiring Attention

| Client / Case | Issue | Owner |

|---|---|---|

| Megan’s friend / new-build case | DIP and ID check completed. Documents requested. Sean to review documents. Paul to complete comments and book recommendation once ready. | Paul / Sean |

| New-build reserved client | Workflow had gone down the wrong path. Client has reserved a new-build unit; documents requested; workflow needs correcting. | Paul / Paula |

| Ramesh | Looking at land / self-build. Referral required to Harry Connor / Buildstore. Indicative fee guidance of roughly **£1,000** to be provided. Follow-up diarised for **2 June 2026**. | Bob / Paul / Anna |

| Fergus Gain / Fergus Kane | Protection task outstanding regarding health questions and whether application has been submitted. Application/status also needs checking. | Paul |

| Robert Thurston | Halifax DIP passed at **85% LTV**. Passport still required. Follow-up diarised for **2 June 2026**. | Paul / Anna |

| Rachel | Active-looking workflow item overdue; status and next step require review. | Paul |

| Raymond | Remortgage reverted to product transfer after down valuation. Protection review still needs follow-up. | Paul / Admin |

| Claire and Callum | Employer benefits details required before protection review can be completed. | Sean |

| Tatiana | Protection review to be arranged with Tatiana and her mother. | Paul / Admin |

| Tomlinson | Insurance already completed; tracker needs updating. | Paul |

| Gilroy | Protection callback booked for **29 May 2026**. Outcome must be logged. | Paul |

| Burgess | Protection callback booked for **28 May 2026 at 12:30**. Entry had been placed incorrectly under Smith and needs correction. | Paul |

| Smith | Incorrect callback entry made under this client. | Paul |

| Emily Irwin | Incorrectly showing under Roland; should be Paul’s case. | Paul |

| Charlotte Morrison | Not recognised during review; status and ownership need confirmation. | Paul |

| Stephen Reed / Stevenson | Appeared on 21-day / protection review list; ownership and status need checking. | Paul |

## Revenue and Pipeline Risks

- May 2026 written business is likely to fall short of the required **17**.

- Purchase activ

[Notes truncated for file size — full notes available in Plaud]

Full transcript

Bob Duncan: Hi Paul. Hi Bob. Just waiting for my camera to load. It&#x27;s saying that you are there, but you are not quite loading yet. There we go. Here you go. I can see you now. I think showing off today. He saw a message from making he is off sec today. Unbelievable. Well, which is about of a shame. But.

Paul Banyard: I think another reason I deserve more money. I&#x27;ve not been off sex since we launched.

Bob Duncan: The brass suck up and get on with it.

Paul Banyard: A trooper you and me.

Bob Duncan: What was it he said? He said he texted me last night, and he says because that&#x27;s about what you&#x27;re doing. He asked how I was doing, and he&#x27;s honestly not great. Not been out of bed, having a toddler has meant I&#x27;ve been ill more in the last twelve months than I have been in the previous ten years. And I just went, Suck up.

Paul Banyard: Catch everything under the sun.

Bob Duncan: Gotta love kids. Let me Why, don&#x27;t you bring up your spreadsheet and hopefully you&#x27;ve updated it for us, Paul? Remember that spreadsheet we discussed last week?

Paul Banyard: You want the twenty-one day one?

Bob Duncan: I want you to look at your twenty-one day. I want to look at the protection callbacks that Mab were doing and your written and bank target for this financial year. So you can bring all three up.

Paul Banyard: Just looking for them. In fact, I think I still need to up. I need to update both of them. In fact, that&#x27;s why am asking you bring them up right twenty one day Paul.

Paul Banyard: I had an issue with the protection calls when the map wasn&#x27;t loading last week, but I should be able to get into it now.

Paul Banyard: Going haywire. Hang on.

Paul Banyard: Hang on. Making a call.

Bob Duncan: Having a nosy.

Paul Banyard: So it looks alright.

Bob Duncan: I&#x27;m on a call, can&#x27;t eat while I&#x27;m on a call. Just nosing to see what it looked like. That&#x27;s just Stephen Reed. Stevenson

Paul Banyard: That one I can&#x27;t remember.

Paul Banyard: What do they call them F S A&#x27;s?

Paul Banyard: I have face. I&#x27;ll suck. Don&#x27;t know why that went out my head.

Bob Duncan: On, what is going on? My sister&#x27;s so oh.

Paul Banyard: Oh.

Speaker 5: Eight Stroke five is just Douglas. I know, and then hold on. I&#x27;ve just got this through T J&#x27;s.

Paul Banyard: Try.

Paul Banyard: Wanted to have a look at it, but if he wanted to look at it, what have you done about it then?

Paul Banyard: I just need to follow up with them getting booked in. Why didn&#x27;t you have the conversation when it was booked in already? It&#x27;s just the way it worked out with the remortgage because we did the remortgage. The property was down valued. Oh no, it&#x27;s above commercial so then we reverted to a PT but I hadn&#x27;t. It was sort of done via email, so I just need to reach out to him. I think he&#x27;d. What I recall we were going to have another look at it, but I doubt there&#x27;ll be anything new. I&#x27;ve already got. Had previously sold them IP and life and kick for the mortgage, and there&#x27;s no change in circumstances.

Paul Banyard: But we&#x27;d catch up. We&#x27;d do it, Raymond&#x27;s like free mortgage.

Paul Banyard: Touching. Yes.

Paul Banyard: This one, Sean was following up with them because we don&#x27;t have details of their employer benefits to have a proper review.

Bob Duncan: Claire and Callum.

Paul Banyard: Yeah, yeah,

Bob Duncan: I don&#x27;t like it&#x27;s been done.

Paul Banyard: Didn&#x27;t even do the mortgage on this.

Bob Duncan: It&#x27;s been done N F E R That&#x27;s the answer to that one.

Paul Banyard: One completed the review. Anything to reschedule?

Paul Banyard: Tatiana is trying to schedule a protection review with her and her mom, because when I did the mortgage review, they said we need to look at protection. Blahdy blah, and the mom&#x27;s employer. Basically, they said, yeah, you need to look at that because you don&#x27;t get anything extra in terms of sick pay benefits just because I am your mom. But I couldn&#x27;t get them booked in at the time. So that&#x27;s some following up with them.

Bob Duncan: So would it make sense for you to follow that up, or for Sean or Holly to follow that up? Is that a good use of your time?

Paul Banyard: I popped up in my workflow yesterday, so I&#x27;ve pinged. I couldn&#x27;t get her on the phone, so I pinged an email because the purchase has now completed. I am going to ask the same question. That would be a short one to get booked in. So get the task assigned number as well. Tomlinson, I didn&#x27;t have on my. I copied and pasted.

Bob Duncan: The list you&#x27;ve done insurance for Tomlinson, haven&#x27;t you?

Paul Banyard: Oh yeah.

Paul Banyard: Couldn&#x27;t think of the name for a minute. Emily.

Paul Banyard: Irwin. I didn&#x27;t have on my list. Emily Irwin is definitely no relation to me

Bob Duncan: Although that&#x27;s not very. That&#x27;s Roland. Is it? That&#x27;s such Roland.

Paul Banyard: That was Roland. I&#x27;ll change that to me because that is definitely me, Emily Irwin. I don&#x27;t recognize Charlotte Morrison. So that is those updated. Go to.

Paul Banyard: Action calls map.

Paul Banyard: Some of these are still to go ahead. I think Gilroy.

Paul Banyard: Where did I see Gilroy?

Paul Banyard: Sure, I saw an. there it is.

Paul Banyard: Just put booked for twenty nine and five twenty six. That&#x27;s this Friday. Ed Neca.

Speaker 5: Maybe walk around because one of them got down to speak out. How about you? I remember this one. Twenty.

Paul Banyard: Twenty four, Burgess.

Bob Duncan: It was going to have been on the Mab callbacks list. So when was it booked in your diary? So be is that being platformed? It won&#x27;t be in Midus.

Paul Banyard: Two twenty eight.

Paul Banyard: Tomorrow. It&#x27;s in tomorrow at.

Paul Banyard: At half twelve.

Paul Banyard: Somebody at my door.

Bob Duncan: You&#x27;ve just put that in the wrong place. You put it under Smith. I&#x27;ll get your door and then I&#x27;ll wait.

Paul Banyard: Cool, two tickets.

Paul Banyard: Back.

Speaker 5: It&#x27;s my sister&#x27;s wedding actually, so don&#x27;t know what to expect. Are you alive? Yeah. Oh fantastic. Thanks for that. Thanks. Actually I&#x27;ll just ask this question, then if you don&#x27;t mind, it&#x27;s the.

Bob Duncan: All up to date? And then what about your business return for the month? Banks.